## Task
UniqueTaskID | ID | Name | BarCode | TaskCode | Code1 | Code2 | Code3 | Code4 | Code5 | Code6 | Code7 | Code8 | Code9 | Code10 | Code11 | Code12 | Code13 | Code14 | Code15 | Code16 | Code17 | Code18 | Code19 | Code20
GBL 36420 | 131196 | Mobilisation |  |  | Code5: Pre Constrution
GBL 36430 | 131201 | Construction Phase Plan |  |  | Code5: Pre Constrution
GBL 36440 | 131202 | Load Bank Cable Route Survey |  |  | Code5: Pre Constrution
GBL 36431 | 131203 | Delap Validation Survey |  |  | Code5: Pre Constrution
GBL 36450 | 131204 | Site Set Up |  |  | Code5: Pre Constrution
GBL 36460 | 131207 | MEP Drawings |  |  | Code5: Design
GBL 36470 | 131208 | Builderswork Drawings |  |  | Code5: Design
GBL 033 | 131229 | Preperation of UPS technical submittal |  |  | Code4: UPS; Code5: Tech Subs
GBL 034 | 131230 | Approval of UPS technical Submittal |  |  | Code4: UPS; Code5: Tech Subs
GBL 035 | 131231 | Manufacture |  |  | Code4: UPS; Code5: Procurement/Manufacturing
GBL 043 | 131239 | Preperation of New Breaker technical submittal |  |  | Code5: Tech Subs
GBL 044 | 131243 | Approval of New Breakers technical Submittal |  |  | Code5: Tech Subs
GBL 045 | 131244 | Manufacture |  |  | Code5: Procurement/Manufacturing
GBL 053 | 131248 | Preperation of Junction Box technical submittal |  |  | Code5: Tech Subs
GBL 054 | 131251 | Approval of Junction Box technical Submittal |  |  | Code5: Tech Subs
GBL 055 | 131253 | Manufacture |  |  | Code5: Procurement/Manufacturing
GBL 072 | 131261 | Preperation of BMS technical submittal |  |  | Code4: BMS & controls; Code5: Tech Subs
GBL 082 | 131262 | Approval of BMS technical Submittal |  |  | Code4: BMS & controls; Code5: Tech Subs
GBL 092 | 131263 | Manufacture |  |  | Code4: BMS & controls; Code5: Procurement/Manufacturing
GBL 024 | 131280 | H&S Plan Preparation and Issue |  |  | Code5: Documentation
GBL 025 | 131281 | Construction Programme Client Approval |  |  | Code5: Documentation
GBL 36480 | 131282 | Construction Programme Preparation and Issue |  |  | Code5: Documentation
GBL 36490 | 131283 | Commissioning Plan Client approval |  |  | Code5: Documentation
GBL 36500 | 131284 | Commissioning Plan Preparation and Issue |  |  | Code5: Documentation
GBL 36510 | 131285 | Commissioning RAMS Approvals |  |  | Code5: Documentation
GBL 36520 | 131286 | Commissioning RAMS Preparation and Issue |  |  | Code5: Documentation
GBL 36530 | 131287 | Construction RAMS Approvals |  |  | Code5: Documentation
GBL 36540 | 131288 | Construction RAMS Preparation and Issue |  |  | Code5: Documentation
GBL 36550 | 131289 | Logistic Plan Client Approval |  |  | Code5: Documentation
GBL 36560 | 131290 | Logistic Plan Preparation and Issue |  |  | Code5: Documentation
GBL 36570 | 131291 | Environmental Plan Client Approval |  |  | Code5: Documentation
GBL 36580 | 131292 | Environmental Plan Preparation and Issue |  |  | Code5: Documentation
GBL 36590 | 131298 | Quality Plan Client Approval |  |  | Code5: Documentation
GBL 36600 | 131299 | Quality Plan Preparation and Issue |  |  | Code5: Documentation
GBL 36610 | 131300 | H&S Plan Client Approval |  |  | Code5: Documentation
GBL 37080 | 131432 | UPS commissioning/SAT & Loadbank |  |  | Code3: Level 3; Code4: UPS; Code5: Commissioning
GBL 37090 | 131433 | Site Test/ Batteries to settle |  |  | Code3: Level 3; Code4: UPS; Code5: Commissioning
GBL 37100 | 131434 | IST |  |  | Code3: Level 5; Code4: UPS; Code5: Commissioning
GBL 37110 | 131437 | UPS commissioning/SAT & Loadbank |  |  | Code3: Level 3; Code4: UPS; Code5: Commissioning
GBL 37120 | 131438 | Site Test/ Batteries to settle |  |  | Code3: Level 3; Code4: UPS; Code5: Commissioning
GBL 37130 | 131439 | IST |  |  | Code3: Level 5; Code4: UPS; Code5: Commissioning
GBL 071 | 131448 | Health and Safety File |  |  | Code5: Close Out & Handover
GBL 081 | 131449 | Record Drawings |  |  | Code5: Close Out & Handover
GBL 091 | 131450 | Operating Manual |  |  | Code5: Close Out & Handover
GBL 101 | 131451 | Client Training |  |  | Code5: Close Out & Handover
GBL 37280 | 132678 | Raise required flooring to allow containment install |  |  | Code3: Level 1; Code4: Flooring; Code5: Construction
GBL 37290 | 132679 | Install containment for Submains/ DC cabling within room |  |  | Code3: Level 1; Code4: Electrical Containment; Code5: Construction
GBL 37300 | 132680 | Installation of containment from UPS output switchboard to MTS in the riser |  |  | Code3: Level 1; Code4: Electrical Containment; Code5: Construction
GBL 37310 | 132681 | Installation of New UPS/ BCB/ Battery Racks/ Batteries |  |  | Code3: Level 1; Code4: UPS; Code5: Construction
GBL 37320 | 132682 | Installation & testing of DC cabling |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37330 | 132683 | Installation of 2No 250A Micrologic 2.2 MCCB's for new UPS supplies to MTS |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37340 | 132684 | Installation of 2No 250A Micrologic 2.2 to exisiting 250A devices A3 and A4 |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37350 | 132685 | Installation of Submains to UPS & output panel to MTS |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37360 | 132686 | Installation of Earthing |  |  | Code3: Level 1; Code4: Earthing installation; Code5: Construction
GBL 37370 | 132687 | Installation of New EMS cabling from the new UPS to EMS switch |  |  | Code3: Level 1; Code4: EMS system; Code5: Construction
GBL 37380 | 132688 | Installation of Junction Box |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37390 | 132689 | Installation of temporary cabling from connection box to new UPS |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37400 | 132690 | Final connections to LV panel/ MTS's and connection box to Admin 2 + shutdown |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37410 | 132691 | Testing of all Submain cabling |  |  | Code3: Level 2; Code4: Electrical testing; Code5: Construction
GBL 37420 | 132693 | Removal of exisiting BMS cabling to exisiting UPS to BMS cabinet + Temporary cabling |  |  | Code4: Cable installation; Code5: Construction
GBL 37430 | 132694 | Removal of exisiting UPS following the successful migration of exisiting circuits to the new UPS |  |  | Code4: UPS; Code5: Construction
GBL 37460 | 132695 | Removal of the UPS frames and plating that are present in the room |  |  | Code4: UPS; Code5: Construction
GBL 37470 | 132696 | Installation of new flooring with pedetals and floor tiles to reinstate raise access floor |  |  | Code4: Flooring; Code5: Construction
GBL 37480 | 132697 | Stultz down flow unit grille adapations to suit new room layout |  |  | Code5: Construction
GBL 37490 | 132698 | Fire Stopping/ Final Decoration |  |  | Code4: Fire-stopping; Code5: Construction
GBL 37500 | 132699 | Removal of Power Factor Correction unit |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37510 | 132700 | Install containment for Submains/ DC cabling |  |  | Code3: Level 1; Code4: Electrical Containment; Code5: Construction
GBL 37520 | 132701 | Installation of New UPS/ BCB/ Battery Racks/ Batteries |  |  | Code3: Level 1; Code4: UPS; Code5: Construction
GBL 37530 | 132702 | Installation & testing of DC cabling |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37540 | 132703 | Installation of 2No 250A Micrologic 2.2 MCCB's for new UPS supplies to MTS |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37550 | 132704 | Installation of 2No 250A Micrologic 2.2 to exisiting 250A devices A3 and A4 |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37560 | 132705 | Installation of Submains to UPS & output panel to MTS |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37570 | 132706 | Installation of Earthing |  |  | Code3: Level 1; Code4: Earthing installation; Code5: Construction
GBL 37580 | 132707 | Installation of New EMS cabling from the new UPS to EMS switch |  |  | Code3: Level 1; Code4: EMS system; Code5: Construction
GBL 37590 | 132708 | Installation of Junction Box |  |  | Code3: Level 1; Code4: Electrical installation; Code5: Construction
GBL 37600 | 132709 | Installation of temporary cabling from connection box to new UPS |  |  | Code3: Level 1; Code4: Cable installation; Code5: Construction
GBL 37610 | 132710 | Testing of all Submain cabling |  |  | Code3: Level 2; Code4: Electrical testing; Code5: Construction
GBL 37620 | 132712 | Removal of exisiting BMS cabling to exisiting UPS to BMS cabinet + Temporary cabling |  |  | Code4: Cable installation; Code5: Construction
GBL 37630 | 132713 | Removal of exisiting UPS following the successful migration of exisiting circuits to the new UPS |  |  | Code4: UPS; Code5: Construction
GBL 37640 | 132714 | Removal of the UPS frames and plating that are present in the room |  |  | Code4: UPS; Code5: Construction
GBL 37650 | 132715 | Installation of new flooring with pedetals and floor tiles to reinstate raise access floor |  |  | Code4: Flooring; Code5: Construction
GBL 37660 | 132716 | Fire Stopping/ Final Decoration |  |  | Code4: Fire-stopping; Code5: Construction
GBL 37441 | 133012 | Switchover from old UPS to new UPS |  |  | Code5: Construction
GBL 37551 | 133016 | Secondary injection test for breakers E6, A8 and B8 |  |  | Code3: Level 2; Code5: Construction
GBL 37341 | 133020 | Secondary injection testing |  |  | Code3: Level 2; Code5: Construction
GBL 37451 | 133029 | Switchover from old UPS to new UPS |  |  | Code5: Construction
GBL 37461 | 133070 | BMS commissioning |  |  | Code3: Level 3; Code5: Commissioning
GBL 37471 | 133074 | BMS commissioning |  |  | Code3: Level 3; Code5: Commissioning
GBL 37351 | 133129 | New Containment route install for extra BMS cables |  |  | Code2: Instructions; Code3: Level 1; Code4: Electrical Containment
GBL 37361 | 133130 | Install New BMS Cables |  |  | Code2: Instructions; Code3: Level 1; Code4: Electrical Containment
GBL 37680 | 133137 | New Containment route install for extra BMS cables |  |  | Code2: Instructions; Code3: Level 1; Code4: Electrical Containment
GBL 37371 | 133138 | Install New BMS Cables |  |  | Code2: Instructions; Code3: Level 1; Code4: Electrical Containment
GBL 37301 | 133143 | Site Closure - Critical Incident |  |  | Code2: Delay Events
GBL 37690 | 133256 | New Containment Route for extra BMS cabling |  |  | Code2: Instructions; Code5: Design
GBL 37700 | 133273 | Quality Assurance |  |  | Code5: QA/QC

## CodeLibrary
Name
GBL Floor Level
Commercial
GBL Commissioning
GBL Cost Code
GBL Project Stage
GBL Area

## CodeLibraryEntry
ID | Name | FullName | ParentName | LibraryName | LibraryID
131166 | Level 5 | Level 5 |  | GBL Commissioning | 131577
131170 | Electrical | Electrical |  | GBL Cost Code | 131578
131606 | Key Dates | Key Dates |  | GBL Project Stage | 131579
131607 | Instructions | Instructions |  | Commercial | 131576
131608 | Level 1 | Level 1 |  | GBL Commissioning | 131577
131609 | Level 2 | Level 2 |  | GBL Commissioning | 131577
131610 | Level 3 | Level 3 |  | GBL Commissioning | 131577
132406 | Delay Events | Delay Events |  | Commercial | 131576
132407 | Level 6 | Level 6 |  | GBL Commissioning | 131577
132408 | Site cleaning / chemical cleaning | Architectural\Site cleaning / chemical cleaning | Architectural | GBL Cost Code | 131578
132409 | Builderswork | Architectural\Builderswork | Architectural | GBL Cost Code | 131578
132410 | Partitioning & whitewalling | Architectural\Partitioning & whitewalling | Architectural | GBL Cost Code | 131578
132411 | Ceilings | Architectural\Ceilings | Architectural | GBL Cost Code | 131578
132412 | Flooring | Architectural\Flooring | Architectural | GBL Cost Code | 131578
132413 | Decorating | Architectural\Decorating | Architectural | GBL Cost Code | 131578
132414 | Plant movement | Architectural\Plant movement | Architectural | GBL Cost Code | 131578
132415 | Craneage | Architectural\Craneage | Architectural | GBL Cost Code | 131578
132416 | Scaffolding | Architectural\Scaffolding | Architectural | GBL Cost Code | 131578
132417 | Bricks, blocks, concrete & plasterboard | Architectural\Bricks, blocks, concrete & plasterboard | Architectural | GBL Cost Code | 131578
132418 | Flooring, carpets & ceilings | Architectural\Flooring, carpets & ceilings | Architectural | GBL Cost Code | 131578
132419 | Windows, doors & accessories | Architectural\Windows, doors & accessories | Architectural | GBL Cost Code | 131578
132420 | Kitchens & furniture | Architectural\Kitchens & furniture | Architectural | GBL Cost Code | 131578
132421 | Drainage | Mechanical\Drainage | Mechanical | GBL Cost Code | 131578
132422 | Tech Subs | Pre Constrution\Tech Subs | Pre Constrution | GBL Project Stage | 131579
132425 | Surveys and Information | Pre Constrution\Surveys and Information | Pre Constrution | GBL Project Stage | 131579
132426 | Procurement/Manufacturing | Pre Constrution\Procurement/Manufacturing | Pre Constrution | GBL Project Stage | 131579
132427 | Delivery | Pre Constrution\Delivery | Pre Constrution | GBL Project Stage | 131579
132428 | Documentation | Pre Constrution\Documentation | Pre Constrution | GBL Project Stage | 131579
132429 | Client Deliveries (MCEs/OFCI) | Pre Constrution\Client Deliveries (MCEs/OFCI) | Pre Constrution | GBL Project Stage | 131579
132430 | Level 4 | Level 4 |  | GBL Commissioning | 131577
132431 | Mechanical | Mechanical |  | GBL Cost Code | 131578
132432 | Architectural | Architectural |  | GBL Cost Code | 131578
132433 | Hygiene equipment | Architectural\Hygiene equipment | Architectural | GBL Cost Code | 131578
132434 | Asbestos removal | Architectural\Asbestos removal | Architectural | GBL Cost Code | 131578
132435 | Fire-stopping | Architectural\Fire-stopping | Architectural | GBL Cost Code | 131578
132436 | Electrical installation | Electrical\Electrical installation | Electrical | GBL Cost Code | 131578
132437 | Cable installation | Electrical\Cable installation | Electrical | GBL Cost Code | 131578
132438 | UPS | Electrical\UPS | Electrical | GBL Cost Code | 131578
132439 | Generators | Electrical\Generators | Electrical | GBL Cost Code | 131578
132440 | Photo-voltaics (including solar panel systems) | Electrical\Photo-voltaics (including solar panel systems) | Electrical | GBL Cost Code | 131578
132441 | CHP (combined heat & power) | Electrical\CHP (combined heat & power) | Electrical | GBL Cost Code | 131578
132442 | Validations & surveys | Electrical\Validations & surveys | Electrical | GBL Cost Code | 131578
132443 | Fire alarm (including disabled refuge / fire telephones systems) | Electrical\Fire alarm (including disabled refuge / fire telephones systems) | Electrical | GBL Cost Code | 131578
132444 | Gas suppression, VESDA & HSSD | Electrical\Gas suppression, VESDA & HSSD | Electrical | GBL Cost Code | 131578
132445 | Lightning protection | Electrical\Lightning protection | Electrical | GBL Cost Code | 131578
132446 | Public address (including voice evacuation) | Electrical\Public address (including voice evacuation) | Electrical | GBL Cost Code | 131578
132447 | Transformers | Electrical\Transformers | Electrical | GBL Cost Code | 131578
132448 | Catering equipment (GBCEL) | Electrical\Catering equipment (GBCEL) | Electrical | GBL Cost Code | 131578
132449 | Data systems | Electrical\Data systems | Electrical | GBL Cost Code | 131578
132450 | Audio visual systems | Electrical\Audio visual systems | Electrical | GBL Cost Code | 131578
132451 | TV & satellite systems | Electrical\TV & satellite systems | Electrical | GBL Cost Code | 131578
132452 | Security systems (including nurse call / disabled alarm ) | Electrical\Security systems (including nurse call / disabled alarm ) | Electrical | GBL Cost Code | 131578
132453 | Busbars | Electrical\Busbars | Electrical | GBL Cost Code | 131578
132454 | Metering & billing systems | Electrical\Metering & billing systems | Electrical | GBL Cost Code | 131578
132455 | Earthing installation | Electrical\Earthing installation | Electrical | GBL Cost Code | 131578
132456 | LV switchgear & PDU's | Electrical\LV switchgear & PDU's | Electrical | GBL Cost Code | 131578
132457 | MV / HV switchgear | Electrical\MV / HV switchgear | Electrical | GBL Cost Code | 131578
132458 | Statutory utilities | Electrical\Statutory utilities | Electrical | GBL Cost Code | 131578
132459 | Strip-out works | Electrical\Strip-out works | Electrical | GBL Cost Code | 131578
132460 | PLC / SCADA package | Electrical\PLC / SCADA package | Electrical | GBL Cost Code | 131578
132461 | Maintenance | Electrical\Maintenance | Electrical | GBL Cost Code | 131578
132462 | EMS system | Electrical\EMS system | Electrical | GBL Cost Code | 131578
132463 | Durasteel | Electrical\Durasteel | Electrical | GBL Cost Code | 131578
132464 | Pre-fabrication - Steelwork / GRP | Electrical\Pre-fabrication - Steelwork / GRP | Electrical | GBL Cost Code | 131578
132465 | Electrical testing | Electrical\Electrical testing | Electrical | GBL Cost Code | 131578
132466 | Miscellanous electical sub-contract | Electrical\Miscellanous electical sub-contract | Electrical | GBL Cost Code | 131578
132467 | Lighitng Control | Electrical\Lighitng Control | Electrical | GBL Cost Code | 131578
132468 | Lighting | Electrical\Lighting | Electrical | GBL Cost Code | 131578
132469 | Mechanical installation | Mechanical\Mechanical installation | Mechanical | GBL Cost Code | 131578
132470 | Plumbing installation | Mechanical\Plumbing installation | Mechanical | GBL Cost Code | 131578
132472 | Ductwork | Mechanical\Ductwork | Mechanical | GBL Cost Code | 131578
132473 | Ductwork (fire-rated) | Mechanical\Ductwork (fire-rated) | Mechanical | GBL Cost Code | 131578
132474 | Insulation | Mechanical\Insulation | Mechanical | GBL Cost Code | 131578
132475 | Insulation (fire-rated) | Mechanical\Insulation (fire-rated) | Mechanical | GBL Cost Code | 131578
132476 | Validations & surveys | Mechanical\Validations & surveys | Mechanical | GBL Cost Code | 131578
132477 | Fire-stopping | Mechanical\Fire-stopping | Mechanical | GBL Cost Code | 131578
132478 | BMS & controls | Mechanical\BMS & controls | Mechanical | GBL Cost Code | 131578
132479 | Gas suppression, VESDA & HSSD | Mechanical\Gas suppression, VESDA & HSSD | Mechanical | GBL Cost Code | 131578
132481 | Air conditioning (VRF / DX) | Mechanical\Air conditioning (VRF / DX) | Mechanical | GBL Cost Code | 131578
132482 | Air handling units | Mechanical\Air handling units | Mechanical | GBL Cost Code | 131578
132483 | Chiller plant | Mechanical\Chiller plant | Mechanical | GBL Cost Code | 131578
132484 | AC plant & refrigeration plant | Mechanical\AC plant & refrigeration plant | Mechanical | GBL Cost Code | 131578
132485 | Public health | Mechanical\Public health | Mechanical | GBL Cost Code | 131578
132486 | Smoke control system | Mechanical\Smoke control system | Mechanical | GBL Cost Code | 131578
132487 | Car park ventilation system | Mechanical\Car park ventilation system | Mechanical | GBL Cost Code | 131578
132488 | Leak detection | Mechanical\Leak detection | Mechanical | GBL Cost Code | 131578
132489 | Refrigerant leak detection | Mechanical\Refrigerant leak detection | Mechanical | GBL Cost Code | 131578
132490 | Medical gases | Mechanical\Medical gases | Mechanical | GBL Cost Code | 131578
132491 | Water treatment & chlorination | Mechanical\Water treatment & chlorination | Mechanical | GBL Cost Code | 131578
132492 | Site cleaning / chemical cleaning | Mechanical\Site cleaning / chemical cleaning | Mechanical | GBL Cost Code | 131578
132493 | Trace heating | Mechanical\Trace heating | Mechanical | GBL Cost Code | 131578
132494 | Metering & billing systems | Mechanical\Metering & billing systems | Mechanical | GBL Cost Code | 131578
132495 | Boiler flue installation | Mechanical\Boiler flue installation | Mechanical | GBL Cost Code | 131578
132496 | CHP flue installation | Mechanical\CHP flue installation | Mechanical | GBL Cost Code | 131578
132497 | Pumps & pressurisation units | Mechanical\Pumps & pressurisation units | Mechanical | GBL Cost Code | 131578
132498 | Underfloor heating | Mechanical\Underfloor heating | Mechanical | GBL Cost Code | 131578
132499 | Fume cupboard ventilation | Mechanical\Fume cupboard ventilation | Mechanical | GBL Cost Code | 131578
132500 | Pipe freezing & hot tapping | Mechanical\Pipe freezing & hot tapping | Mechanical | GBL Cost Code | 131578
132501 | Statutory utilities | Mechanical\Statutory utilities | Mechanical | GBL Cost Code | 131578
132502 | Strip-out works | Mechanical\Strip-out works | Mechanical | GBL Cost Code | 131578
132503 | Sprinkler installation | Mechanical\Sprinkler installation | Mechanical | GBL Cost Code | 131578
132504 | Maintenance | Mechanical\Maintenance | Mechanical | GBL Cost Code | 131578
132505 | Water misting system | Mechanical\Water misting system | Mechanical | GBL Cost Code | 131578
132506 | Boilers, cylinders & plant | Mechanical\Boilers, cylinders & plant | Mechanical | GBL Cost Code | 131578
132507 | Dry / wet riser system | Mechanical\Dry / wet riser system | Mechanical | GBL Cost Code | 131578
132508 | Irrigation / water harvesting / solar HWS systems | Mechanical\Irrigation / water harvesting / solar HWS systems | Mechanical | GBL Cost Code | 131578
132509 | Pre-fabrication / packaged plant rooms | Mechanical\Pre-fabrication / packaged plant rooms | Mechanical | GBL Cost Code | 131578
132510 | Pre-fabrication - Steelwork / GRP | Mechanical\Pre-fabrication - Steelwork / GRP | Mechanical | GBL Cost Code | 131578
132511 | Mechanical testing | Mechanical\Mechanical testing | Mechanical | GBL Cost Code | 131578
132513 | Pre Constrution | Pre Constrution |  | GBL Project Stage | 131579
132514 | Construction | Construction |  | GBL Project Stage | 131579
132515 | Commissioning | Commissioning |  | GBL Project Stage | 131579
132516 | Close Out & Handover | Close Out & Handover |  | GBL Project Stage | 131579
132544 | Basement | Basement |  | GBL Floor Level | 35
132546 | Ground Floor | Ground Floor |  | GBL Floor Level | 35
132547 | First Floor | First Floor |  | GBL Floor Level | 35
132548 | Second Floor | Second Floor |  | GBL Floor Level | 35
132549 | Third Floor | Third Floor |  | GBL Floor Level | 35
132550 | Roof | Roof |  | GBL Floor Level | 35
132552 | Gantry | Gantry |  | GBL Area | 132542
132553 | Plantroom | Plantroom |  | GBL Area | 132542
132554 | Powerstream | Powerstream |  | GBL Area | 132542
132555 | Data Hall | Data Hall |  | GBL Area | 132542
132556 | MMR Room | MMR Room |  | GBL Area | 132542
132558 | Storage Room | Storage Room |  | GBL Area | 132542
132560 | Electrical Containment | Electrical\Electrical Containment | Electrical | GBL Cost Code | 131578
133109 | Battery Room | Battery Room |  | GBL Area | 132542
133258 | Design | Design |  | GBL Project Stage | 131579
133274 | QA/QC | QA/QC |  | GBL Project Stage | 131579